# Course Setup

# Responsibility Timeline & Checklist

I’m excited to share that we’re one step closer toward your Mental Health First Aid Course. Insert introduction of instructor(s) here.

These are the details we know thus far:

- Curricula:

- Course Type:

- Location:

- Date:

- Audience:

- Funding:

Below you will find a Timeline/Checklist to help ensure a successful training.

REMINDER: If at any time you are not receiving responses from your instructor(s) or your Host, please notify info@mhfamissouri.org.

Thanks for making a difference in your community!

MHFA Missouri

# Responsibility Timeline & Checklist:

## One to two months before the course:

- Host/Instructor - Schedule a brief meeting or call between the instructor/Host. The instructor will walk you through the following course details:

  - Confirm agenda timeline including any breaks/lunch. Hours below do not include breaks.

    - In-Person: 6.5 hours for Youth MHFA and 7.5 hours for Adult MHFA.

    - Blended: 2 hours self-paced online learning, followed by 4.5 hours Youth MHFA or 5.5 hours Adul MHFA in-person course

    - Virtual: 2 hours self-paced online learning, followed by 4.5 hours Youth MHFA or 5.5 hours Adult MHFA live virtual training

  - Participant Communication Plan

    - Confirm who will be responsible for corresponding with the participants including for following up with participants who have not started or have not completed the required pre-work/pre-tests. 2 hours of pre-work is required for blended courses, about 5-10 minutes of pre-tests are required for in-person courses.

      - Pro-tip: consider adding 10 minutes to the start of an in-person class for participants to complete pre-tests if you’re concerned they may not do it in advance.

    - Participant technology requirements (Virtual)

      - Computer with microphone and speakers

      - HD webcam

      - Internet speed of at least 5Mbps (test your internet speed at www.speedtest.net)

    - Participant Accommodations (From NCMW)
The MHFA and Y/MHFA course content and materials were designed to align with 508 compliance standards for accessibility and can be read by JAWS and NVDA screen reading software. MHFA Connect learning is compatible with JAWS and NVDA screen reading software.

You will receive an invitation to create an account in Connect after which we give you access to your pre-work.  If you find that you cannot access course materials, please let us know, and we can work with you to assist with your needs.

    - Participants should understand course attendance/participation expectations: Required pre-work must be completed prior to the course date.The course is a small group interactive training. Participants should be present for 100% of the course and actively engaged (not completing other work or having other responsibilities).

  - Materials/ Physical space (for courses with an in-person instructor-led training)

    - Determine who is responsible for providing printed Participant Processing Guides (PPGs).  If the Host cannot cover copying costs, the instructor stipend may be used to cover costs.

      - Pro tip: Consider printing only required pages of the guide if printing cost is prohibitive

    - Discuss room set-up details such as table/chair arrangements, when will the instructor(s) have access to the room, are there parking/building access considerations instructors need to know

    - A/V Equipment. Who will provide the required equipment: projector, projection screen, and speakers.

    - Shipping of manuals- For fully in-person courses where should manuals be mailed?

    - Wifi- Is wifi available in the training space? If not, instructors should be prepared with fully downloaded videos.

    - Other materials: discuss other materials like post-it notes, markers, flip chart paper.

- Host - Reserve training location for courses with an in-person instructor-led training

- Host - Will begin advertising, if necessary

- Host - Will be responsible for registration. Registration should include the participant's first and last name, unique email address (will be used for their username), cell phone number (required for virtual courses).

## Two-three weeks before the course:

- Host - Submit roster to instructor, including first/last name and email

- Instructor - Create course in MHFA Connect as well as create and add participants (Create User Guide). Instructor note: we recommend this over inviting and then enrolling users.

- Instructor - Send info@mhfamissouri.org screenshots of the course and course roster and shipping address for manual purchase. Include the course type ( (in-person only)

- Host/Instructor - after previous step, correspond with participants to invite them to begin their pre-work/pre-test
Connect Email Template to Enroll Learners: https://drive.google.com/file/d/13fQAHoTK0ty18MIMvuWTVdav0VHGZs3D/view?usp=sharing

## One week before the course:

- Instructor - should check on pre-work during this week and communicate with either the participants and/or Host to assist participants with completion (blended only)

- Instructor  - Assist participants with completion of pre-course evaluation and opinions quiz before the ILT session.  This can be done day-of, before the course begins if extra time is alloted.  (in-person only)

## Post Course:

- Instructor - Responsible for taking attendance and updating the course roster in MHFA Connect and removing any participants who did not complete the course. See step 12 (pg 25) in MHFA Connect User Guide.

- Host/Instructor - Send a post-course email. Include any Host or local resources.

- Instructor (for blended/virtual courses)- Forward invoice from the National Council with the payment link to info@mhfamissouri.org within 1 week of the course. Include the Host, course date, instructor(s) and actual number of participants. Please submit a Request Assistance form in MHFA Connect if you do not receive it. The stipend payment process will be initiated only after receiving this.

- Instructor (in person courses)- Email info@mhfamissouri.org with the Host, course date, instructor(s) and actual number of participants. The stipend payment process will be initiated only after receiving this.